## Project Plan
| Project Plan |  | July |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
1. Plan & Scope |  | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12 | w13 | w14 | w15 | w16 | w17 | w18 | w19 | w20
Prepare project structure | bar: July w3 to July w4
| Define Scope of work | [23 empty] | ABC | bar: July w3 to July w4
| Develop project master plan | [23 empty] | Visan | bar: July w3 to July w4
| Define project committee | [23 empty] | ABC & Visan Team | bar: w2
| System infrastructure | [23 empty] | Customer
HW preparation | bar: July w1 to Aug w4
NW preparation | bar: July w1 to Aug w4
System installation and test | bar: July w1 to Aug w4
2. Define
Prerequisite
send checklist/questionaire
Review document
Requirement definition
Understand formula definition | bar: July w1 to July w2
Understand source of data | bar: July w1 to July w2
Customer report review
Requirement definition final | bar: Aug w3
Acceptance requirement Definition | bar: Aug w4
3. Design
Design screen/reports | bar: Aug w3 to Aug w4
Design flowchart | bar: Aug w3 to Aug w4
Acceptance design | bar: Aug w5
4. Develop
Database Define
Master File preparation | bar: Aug w5
Customer review | bar: Aug w6
| Coding | Sep w8: รายงานเลี้ยงรุ่นไก่; Oct w12: ต้นทุนไก่
Present prototype | bar: Sep w10; Oct w14
Acceptance prototype | bar: Oct w11; Nov w15
5. Testing/Deploy
Training
Prepare training material | bar: Oct w14
Training class | bar: Nov w15
Workshop
Customer prepare test case | bar: Nov w16
User acceptance test | bar: Nov w17
Go Live
Test month-end import data | bar: Nov w18
Result verification | bar: Nov w18 to Dec w19
Report generation and verification | bar: Nov w18
Acceptance Live On | bar: Nov w18 to Dec w19
Post Implmentation
Checking completion | bar: Dec w20
Project sign-off | bar: Dec w20

## Sheet2
| w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12 | w13 | w14 | w15 | w16 | w17 | w18 | w19 | w20
Mandatory
Plan
Analyze
Design
Build
Test